## Task Master List
ID | Source | Section | Status | Lane | Branch | Title | Description | Keep_Y_N_Maybe | Your_Notes
TQ-001 | TASK_QUEUE.md | Ongoing | Paused | Backend | fix/cleanup | Task 5 — Facility balance & content | Run facility sim (balance_sim_facility.ts) to tune win rate and fight cliffs. Target 25-40% skilled full-clear in real play. Paused until post-UI finalize. Flat sim ~1.7% is reference only.
TQ-002 | TASK_QUEUE.md | Ongoing | Ongoing | UI | feat/ui-redesign / codex/* | Parallel UI polish | Direction-05 visual pass across battle / reward / evolution / unit-select readability. Separate from backend pass.
TQ-003 | TASK_QUEUE.md | Data | Done | Data | fix/cleanup | Task 13 — Picker blurbs (data) | All 8 heroes have pickerBlurb + pickerCategory in heroes.data.json; DataManager loads them.
TQ-004 | TASK_QUEUE.md | Data | Done | Data | fix/cleanup | Task 11 — Evolution callsigns | 8 base + 16 evo callsigns in data; applied on evolve in GameState.gd.
TQ-005 | TASK_QUEUE.md | Data | Done | Data | fix/cleanup | Task 12 — Normalize eff text | audit_eff_text.py --apply yields 0 mismatches between eff strings and ability fields.
TQ-006 | TASK_QUEUE.md | Data | Done | Data | fix/cleanup | Facility fight 7 roster | Fight 7 enemy order: Rust Drone → Heavy Warden → Rust Drone in battle-modes.json.
TQ-007 | TASK_QUEUE.md | Data | Done | Data | fix/cleanup | Trench Rig — Stabilize | Stabilize ability: ally-targeted 10 heal; Avalanche pickerBlurb updated.
TQ-008 | TASK_QUEUE.md | Data | Done | Data | fix/cleanup | Splice Medic — tier-1 kit | Zone reshuffle; Diagnostic/Infusion heals+rolls; Shock Therapy 20 dmg overload.
TQ-009 | TASK_QUEUE.md | Data | Done | Data | fix/cleanup | Splice Medic — Combat Medic evo tune | Triage / Suppression Heal / Surge Revive (70%) tuned in heroes.data.json.
TQ-010 | TASK_QUEUE.md | Data | Done | Data | fix/cleanup | Splice Medic — Synth Warden evo tune | Overclock / Emergency Protocol / Adrenaline Surge / Mass Revival (30%) tuned.
TQ-011 | TASK_QUEUE.md | Data | Done | Data | fix/cleanup | Guard — Bulwark Link | shieldAllyAll: true for squad-wide enemy shield on Bulwark Link.
TQ-012 | TASK_QUEUE.md | Data | Done | Data | fix/cleanup | Resonance Cascade — relic copy | Clearer player-facing desc for dotAmplified relic in relics.data.json.
TQ-013 | TASK_QUEUE.md | Data | Done | Data | fix/cleanup | Reward ladder reference doc | docs/reward-draft-rarity.md documents reward draft rarity rules.
TQ-014 | TASK_QUEUE.md | UI | After UI finalization | UI | feat/ui-redesign | Task 13 — Show picker blurbs on UnitSelect | Wire UnitData.picker_blurb into home_screen.gd detail panel. Blocked until UnitSelect/detail chrome is locked.
TQ-015 | TASK_QUEUE.md | UI | Done | UI | main | Gear equip target — evolved name | Reward gear picker uses GameState.get_run_unit_data() + battle_name() for evolved unit labels.
TQ-016 | TASK_QUEUE.md | UI | Done | UI | main | Enemy shieldAllyAll display | Single squad-wide shield pip for shieldAllyAll abilities (not 6 + 6A split chips).
TQ-017 | TASK_QUEUE.md | UI | Done | UI | main | Ally roll buff visuals (green dice) | Positive rfm on heroes uses green roll_up pip; enemy strip keeps yellow roll_down.
TQ-018 | TASK_QUEUE.md | UI | Done | UI | main | Capped die for RFE (Option A) | Tray lands effective face once at settle; raw kept for crit/overload; post-roll snap removed.
TQ-019 | TASK_QUEUE.md | UI | Tabbed | UI | feat/ui-redesign | Task 8 — Battle feedback / game feel | Hit pause / lunge / shake / overload / death SFX done. Remaining ANIMATION.md Tier 1-3 touches card layout — resume after UI chrome locks.
TQ-020 | TASK_QUEUE.md | UI | Done | UI | main | Death SFX timing | Fatal death SFX at hit moment; skip lead/pause on kills; poison ticks own feedback group.
TQ-021 | TASK_QUEUE.md | UI | Done | UI | main | Task 9 — Audio system | AudioManager wired; SFX tiers per AUDIO.md; hooked to Task 8 events.
TQ-022 | TASK_QUEUE.md | UI | Open | UI | main | Incoming target indicators | During hero targeting show low-key who each enemy is aimed at (pip / connector / subtitle). Readable at 450x1000.
TQ-023 | TASK_QUEUE.md | UI | Tabbed — Claude | UI | main | HP preview — heal before damage | Three playtest bugs: DoT preview sticks; blastAll previews gated until manual target pick; heal+dmg net HP bar/label disagree. See TASK_QUEUE handoff section.
TQ-024 | TASK_QUEUE.md | UI | Done | UI | main | Ability target scope clarity | SELF / ALL scope vocabulary; no trailing ALLY badge; blastAll dmg shows ALL.
TQ-025 | TASK_QUEUE.md | UI | Done | UI | main | Ability readout — bracket scope + superscript | EffectPip notation )value( / (value) / plain + superscript duration on dice tray and card pips.
TQ-026 | TASK_QUEUE.md | UI | Ongoing | UI | main | Card proportion / readability | Tune portrait vs HP vs status at 450x1000 in compact_unit_card.gd and BATTLE_UI_V2_SPEC §19.
TQ-027 | TASK_QUEUE.md | UI | Ongoing | UI | main | Reward / evolution visual consistency | Shared PersistentHeader; polish pass so reward and evolution match battle chrome.
TQ-028 | TASK_QUEUE.md | UI | Dropped | UI | main | V2 band geometry audit | Center band 540px is intentional; no Task 3 geometry pass needed.
TQ-029 | TASK_QUEUE.md | UI | Optional | UI | main | Protocol footer chrome extract | Optional refactor: extract protocol footer from battle scene into reusable component. Not formally queued.
TQ-030 | TASK_QUEUE.md | UI | Optional | UI | main | Help overlay extract | Optional refactor: extract help overlay. Not formally queued.
TQ-031 | TASK_QUEUE.md | Combat | Done | Backend | fix/cleanup | Evolution XP (D2) | 100 XP gate; 20+avg_roll alive / avg_roll dead; one evolution per battle win + deferred FIFO queue.
TQ-032 | TASK_QUEUE.md | Combat | Done | Backend | fix/cleanup | Revive pct + reviveAll | revivePct and reviveAll in schema + combat_manager.gd for medic evos.
TQ-033 | TASK_QUEUE.md | Combat | Done | Backend | fix/cleanup | Gear/relic ability audit regressions | 12 gear/relic effect handlers covered in AbilityAuditRunner.tscn.
TQ-034 | TASK_QUEUE.md | Combat | Paused | Backend | fix/cleanup | Task 5 — Facility balance (sim) | Same as TQ-001. Sim tuning deferred until finalize pass.
TQ-035 | TASK_QUEUE.md | Parking lot | Parked | UI | main | Task 14 — Enemy half-cards | Compact/half-height enemy cards when 4-5 enemies in fight. Current 3-enemy layout is priority.
TQ-036 | TASK_QUEUE.md | Parking lot | Parked | Backend | fix/cleanup | Task 7 — Rename dot to burn | Lockstep rename dot/poison to burn across data combat sim audits UI. Large touch surface; one session only.
TQ-037 | TASK_QUEUE.md | Parking lot — Design | Pinned | Design |  | Facility full-clear target (D1) | Design pin: 25-40% skilled full-clear in real play with items/protocol/relic. Flat sim ~1.7% is lab reference only.
TQ-038 | TASK_QUEUE.md | Parking lot — Design | Done | Design |  | Evolution XP (D2) design pin | Design decision locked and implemented. See TQ-031.
TQ-039 | TASK_QUEUE.md | Parking lot — Design | Deferred | Design |  | Shield hero viability (D3) | Leave shield hero kit as-is until finalize pass + richer sim.
TQ-040 | TASK_QUEUE.md | Parking lot — Design | Deferred | Design |  | Sim expansion (items/protocol/relic) | No new sim scope until later finalize pass.
TQ-041 | TASK_QUEUE.md | Parking lot — Design | Not an issue | Design |  | Round 5 relic duplicate | Relics only drop after fight 5; one relic per run — not a bug.
TQ-042 | TASK_QUEUE.md | Parking lot — Design | Not scheduled | Backend |  | Mark / vulnerable keyword | markNext keyword: combat_manager + schema + sample abilities. Not scheduled.
TQ-043 | TASK_QUEUE.md | Parking lot — Design | Dropped | Backend |  | Sim — full protocol economy | gainProtocol charge pool in sim is sufficient; full economy sim dropped.
TQ-044 | TASK_QUEUE.md | Parking lot — Design | Not scheduled | Backend |  | ARC electric status | Option A force roll 1 vs Option B zone bump for ARC electric. Not scheduled.
TQ-045 | TASK_QUEUE.md | Parking lot — Design | Open | Design |  | Demo scope | Decide: all 5 operations in demo vs facility-first demo scope.
TQ-046 | TASK_QUEUE.md | Parking lot — Design | Far future | Design |  | Third evolution / stats (STR/DEX/INT) | Far-future design — not planned.
TQ-047 | TASK_QUEUE.md | Parking lot — Design | Partial | Backend |  | Wraith Engineer protocol efficiency | Manipulation discounts partially done; Overclocked generator done; rest TBD.
TQ-048 | TASK_QUEUE.md | Parking lot — Design | Pinned | UI |  | Ability target scope labels | Display vocabulary SELF / ALLY / ALL only. Mostly implemented via EffectPip; doc pin remains.
TQ-049 | TASK_QUEUE.md | Completed (reference) | Done | Meta |  | Doc drift (Task 0) | CLAUDE.md GDD.md ROADMAP.md reconciled to GROUND_TRUTH.
TQ-050 | TASK_QUEUE.md | Completed (reference) | Done | Meta |  | Baseline (Task 1) | docs/BASELINE.md + tag baseline-fable-restart + ability audit baseline.
TQ-051 | TASK_QUEUE.md | Completed (reference) | Done | Backend |  | Task 2 — battle_scene split | battle_layout.gd battle_card_view.gd battle_feedback.gd extracted from monolith.
TQ-052 | TASK_QUEUE.md | Completed (reference) | Done | Backend |  | Task 4 — Ability audit | 78+ passed Godot; 0 Python keyword gaps at time of completion.
TQ-053 | TASK_QUEUE.md | Completed (reference) | Done | Backend |  | Sim gainProtocol | Charge pool in battle-progress-sim.lib.ts for protocol in sims.
TQ-054 | TASK_QUEUE.md | Completed (reference) | Done | Backend |  | Task 6 — Gear & relic effects | 14 Task-6 effect types wired; audit_gear_relic_effects.py clean.
TQ-055 | TASK_QUEUE.md | Completed (reference) | Done | Backend |  | Task 10 — Protocol economy | Cap 10 +1/turn nudge/reroll/set costs; Protocol Override cost 0.
TQ-056 | TASK_QUEUE.md | Completed (reference) | Done | Backend |  | Hygiene — project.godot tmp | Untracked Godot editor temp files removed from git index.
TQ-057 | TASK_QUEUE.md | Completed (reference) | Done | Backend |  | Facility backend merge | Validation Scrapmaster P2 boss P2 rules merged.
TQ-058 | TASK_QUEUE.md | Completed (reference) | Done | Data |  | Data batch Jun 2026 | Facility fight 7 medic/trench/guard/relic JSON; revivePct/reviveAll schema.
TQ-059 | TASK_QUEUE.md | Completed (reference) | Done | UI |  | EffectPip centralization | Central effect pip module for abilities gear relics items + EFFECT_PIP_GUIDE.md.
TQ-060 | TASK_QUEUE.md | Completed (reference) | Done | UI |  | Battle targeting highlights | Team dither borders gold active picker bright pending hero names. Jun 2026.
UIB-001 | UI_BACKLOG.md | §1 Encounter carousel | Done | UI | main | Boss image right of data | Encounter carousel shows boss portrait to the right of encounter text. Done 855c60c.
UIB-002 | UI_BACKLOG.md | §1 Encounter carousel | Done | UI | main | Carousel nav buttons half height | Encounter carousel prev/next buttons reduced to half height. Done 855c60c.
UIB-003 | UI_BACKLOG.md | §2 Squad picker | Done | UI | main | Larger SELECT ENCOUNTER / SELECT SQUAD headers | Picker header typography enlarged. Done 855c60c.
UIB-004 | UI_BACKLOG.md | §2 Squad picker | Done | UI | main | Larger description font | Larger font for encounter and unit detail blurbs. Done 855c60c.
UIB-005 | UI_BACKLOG.md | §2 Squad picker | Done | UI | main | Remove 3 OF 8 from squad header | Removed slot count from SELECT SQUAD header line. Done 855c60c.
UIB-006 | UI_BACKLOG.md | §2 Squad picker | Done | UI | main | Focus tag top-right | Control/Offense/Defense tag moved to top-right of unit box. Done 855c60c.
UIB-007 | UI_BACKLOG.md | §2 Squad picker | Done | UI | main | Remove slot-number badges | Removed 1/2/3 slot badges; cyan selection highlight is enough. Done 855c60c.
UIB-008 | UI_BACKLOG.md | §3 Content copy | Open — may be done | Data | main | Rewrite unit pickerBlurbs | Concise hero blurbs in heroes.data.json — no evolution info no em dashes. Data updated Jun 2026; confirm and check off backlog.
UIB-009 | UI_BACKLOG.md | §3 Content copy | Open — may be done | Data | main | Rewrite operation blurbs/victorySub | Concise operation blurbs in battle-modes.json — no boss names in blurb. Data updated Jun 2026; confirm and check off backlog.
UIB-010 | UI_BACKLOG.md | §4 Unit detail popup | Open | UI | main | MORE button — full unit detail popup | Add MORE button on picker detail bar opening popup with full ability/roll breakdown.
UIB-011 | UI_BACKLOG.md | §4 Unit detail popup | Open | UI | main | Battle long-press → same detail popup | Long-press portrait in battle opens same unit detail screen; needs sizing layout typography TLC.
UIB-012 | UI_BACKLOG.md | §4 Unit detail popup | Open | UI | main | Separate view info from select unit | Design flow to browse unit details without auto-selecting for squad — minimal extra clicks. Design task first.
UIB-013 | UI_BACKLOG.md | §5 Battle targeting | Done | UI | main | Target highlight = team border color | Legal targets use DT_ENEMY_DITHER / DT_HERO_DITHER; active picker gold border; no layout shift.
UIB-014 | UI_BACKLOG.md | §5 Battle targeting | Done | UI | main | No portrait gray for non-targeting heroes | Bright portrait always; pending heroes get bright name; active picker normal name + gold border.
UIB-015 | UI_BACKLOG.md | §5 Battle targeting | Open — mostly done | UI | main | Better ability scope/keyword display | All/Self/duration/keyword clarity. Mostly EffectPip; may need status chip + tooltip pass at 450x1000.
UIB-016 | UI_BACKLOG.md | §6 Tooltips | Open | UI | main | Update hover long-descriptions | Refresh dice rollover ability-pip rollover and status rollover tooltips for new UI context.
SPEC-001 | BATTLE_UI_V2_SPEC.md | §19 Open tuning | Ongoing | UI | main | Card proportion balance | Final balance between portrait band HP band and status band on compact unit cards.
SPEC-002 | BATTLE_UI_V2_SPEC.md | §19 Open tuning | Ongoing | UI | main | Unit name sizing | Phone-readable unit name font/size at 450x1000 preview scale.
SPEC-003 | BATTLE_UI_V2_SPEC.md | §19 Open tuning | Ongoing | UI | main | HP number readability | HP text legible over the HP bar fill.
SPEC-004 | BATTLE_UI_V2_SPEC.md | §19 Open tuning | Ongoing | UI | main | Status region density | Status chip row density and clarity on unit cards.
SPEC-005 | BATTLE_UI_V2_SPEC.md | §19 Open tuning | Ongoing | UI | main | Readout overflow (two-row abilities) | Ability readout behavior when abilities need two pip rows — no spill past dice tray.
SPEC-006 | BATTLE_UI_V2_SPEC.md | §19 Open tuning | Ongoing | UI | main | Button/header/footer polish | Final polish on battle chrome after card readability pass is stable.
HAND-001 | CURSOR_HANDOFF.md | Open work — STALE | Open | UI | feat/ui-redesign | Task 13 show picker blurbs | Duplicate of TQ-014. Handoff doc not updated since audio/targeting work.
HAND-002 | CURSOR_HANDOFF.md | Open work — STALE | Tabbed | UI | feat/ui-redesign | Task 8/9 animation + audio | STALE: Task 9 done. Task 8 partially done. Update or remove from handoff.
HAND-003 | CURSOR_HANDOFF.md | Open work — STALE | Parked | UI | feat/ui-redesign | Task 14 enemy half-cards | STALE: moved to parking lot TQ-035. Update handoff.
HAND-004 | CURSOR_HANDOFF.md | Open work — STALE | Open | UI | feat/ui-redesign | Incoming target indicators | Duplicate of TQ-022.
HAND-005 | CURSOR_HANDOFF.md | Open work — STALE | Ongoing | UI | feat/ui-redesign | Finish Direction-05 UI on branch | Generic polish item; commit battle_scene.gd WIP mentioned in handoff — verify if still relevant.
HAND-006 | CURSOR_HANDOFF.md | Open work — STALE | Paused | Backend | fix/cleanup | Task 5 facility balance sim | Duplicate of TQ-001 / TQ-034.
HAND-007 | CURSOR_HANDOFF.md | Open work — STALE | Not started | Backend | fix/cleanup | Tier 3 sim full run loop | Optional sim with full run loop + rewards — discussed not started.
ROAD-001 | ROADMAP.md | Priority A | Ongoing | UI | main | Battle UI readability (theme) | Active highest-value track: card proportions portrait/HP/status hierarchy phone readability. Overlaps TQ-026 and SPEC-001–006.
ROAD-002 | ROADMAP.md | Priority B | Ongoing | UI | main | Shared in-match UI consistency | Battle reward evolution share header framing tooltips typography. Overlaps TQ-027.
ROAD-003 | ROADMAP.md | Priority C | Ongoing | UI | main | Reward and evolution polish | Reward/evolution UX cleanup and consistency with battle. Overlaps TQ-027.
ROAD-004 | ROADMAP.md | Goal 1 | Ongoing | UI | main | Stabilize battle card readability | Sub-goals: unit names HP band portrait proportion status band. Success = readable at 450x1000.
ROAD-005 | ROADMAP.md | Goal 2 | Ongoing | Process |  | Screenshot-driven visual discipline | Compile-check + regenerate screenshot + honest visual eval for any battle visual change. Process goal not a feature.
ROAD-006 | ROADMAP.md | Goal 3 | Ongoing | Meta |  | Keep agent docs current | Maintain AI_AGENT_GAME_REFERENCE.md and BASELINE.md after merges. Partially done Jun 2026.
ROAD-007 | ROADMAP.md | Medium-Term A | Ongoing | Backend | main | Mechanic cleanup confidence | Validate dice physics; targeting equivalence cards vs dice; reduce battle_scene fragility.
ROAD-008 | ROADMAP.md | Medium-Term B | Ongoing | Art | main | Asset swap polish | Replace legacy placeholder art; align borders/backgrounds; avoid frame clutter.
ROAD-009 | ROADMAP.md | Medium-Term C | Ongoing | UI | main | Cross-screen consistency | Home battle reward evolution run-end should feel like one game not stitched prototypes.
ROAD-010 | ROADMAP.md | Long-Term A | Far future | UI | main | Final art pass | Final card styling header/footer pip/readout language background harmony after proportions stable.
ROAD-011 | ROADMAP.md | Long-Term B | Far future | Backend |  | Full-content confidence | Broader operation coverage reward pool validation evolution-path confidence long-form balance testing.
MISC-001 | (session notes) | Not in queue | Open | UI | main | Migrate build_effect_chips | Legacy emoji chips in battle_card_view.build_effect_chips() for unwired ability-chart UI. Migrate to EffectPip or delete when detail popup built.
MISC-002 | (session notes) | Not in queue | Open | Meta |  | Prune and dedupe task docs | User audit: merge TASK_QUEUE UI_BACKLOG ROADMAP handoff into one maintained list; mark stale items; remove completed reference bloat.
MISC-003 | (session notes) | Not in queue | Open | Meta |  | Update CURSOR_HANDOFF.md | Handoff open-work section is stale (audio done half-cards parked targeting done). Sync or point only to TASK_MASTER_LIST.csv.